{"text_format":"3","workbook":"xls","n_sheets":7,"sheets":["任务_表","Measurement","SystemToolAndRuleEditor","Report","资源_表","工作分配_表","信息_表"],"not_rendered":{"images":5},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"任务_表","index":0,"n_rows":35,"n_cols":7,"rows_kept":35,"hidden":true,"flags":["formulas_cached_only"]}
["标识号","名称","工期","开始时间","完成时间","前置任务","备注"]
[1,"Inception-确定项目范围",{"v":50,"d":"50.d"},"2019-10-29T08:00:00","2020-01-06T17:00:00"]
[2,"需求搜集整理",{"v":10,"d":"10.d"},"2019-10-29T08:00:00","2019-11-11T17:00:00"]
[3,"确定初步软件架构",{"v":5,"d":"5.d"},"2019-11-12T08:00:00","2019-11-18T17:00:00","2"]
[4,"软件操作场景描述（用例分析）",{"v":20,"d":"20.d"},"2019-11-19T08:00:00","2019-12-16T17:00:00","3"]
[5,"UI原型设计",{"v":10,"d":"10.d"},"2019-11-19T08:00:00","2019-12-02T17:00:00"]
[6,"操作路径描述（用例实现路径描述）",{"v":10,"d":"10.d"},"2019-12-03T08:00:00","2019-12-16T17:00:00","5"]
[7,"建立初步模型",{"v":10,"d":"10.d"},"2019-12-17T08:00:00","2019-12-30T17:00:00","4"]
[8,"建立初步类模型（静态模型）",{"v":5,"d":"5.d"},"2019-12-17T08:00:00","2019-12-23T17:00:00"]
[9,"建立初步顺序图模型（动态模型）",{"v":5,"d":"5.d"},"2019-12-24T08:00:00","2019-12-30T17:00:00","8"]
[10,"进度计划编制",{"v":5,"d":"5.d"},"2019-12-31T08:00:00","2020-01-06T17:00:00","7"]
[11,"Elaboration ",{"v":55,"d":"55.d"},"2020-01-07T08:00:00","2020-03-23T17:00:00"]
[12,"更多的操作场景描述（用例分析）",{"v":20,"d":"20.d"},"2020-01-07T08:00:00","2020-02-03T17:00:00"]
[13,"UI原型设计",{"v":10,"d":"10.d"},"2020-01-07T08:00:00","2020-01-20T17:00:00","10"]
[14,"操作路径描述（用例实现路径描述）",{"v":10,"d":"10.d"},"2020-01-21T08:00:00","2020-02-03T17:00:00","13"]
[15,"建立详细模型",{"v":20,"d":"20.d"},"2020-02-04T08:00:00","2020-03-02T17:00:00","12"]
[16,"静态模型",{"v":10,"d":"10.d"},"2020-02-04T08:00:00","2020-02-17T17:00:00"]
[17,"动态模型",{"v":10,"d":"10.d"},"2020-02-18T08:00:00","2020-03-02T17:00:00","16"]
[18,"确定软件最终结构",{"v":15,"d":"15.d"},"2020-03-03T08:00:00","2020-03-23T17:00:00","15"]
[19,"确定软件结构",{"v":10,"d":"10.d"},"2020-03-03T08:00:00","2020-03-16T17:00:00"]
[20,"确定软件UI",{"v":5,"d":"5.d"},"2020-03-17T08:00:00","2020-03-23T17:00:00","19"]
[21,"Construction",{"v":70,"d":"70.d"},"2020-03-24T08:00:00","2020-06-29T17:00:00"]
[22,"数据存储结构设计/开发",{"v":20,"d":"20.d"},"2020-03-24T08:00:00","2020-04-20T17:00:00"]
[23,"设计开发",{"v":10,"d":"10.d"},"2020-03-24T08:00:00","2020-04-06T17:00:00","20"]
[24,"数据存储性能测试",{"v":10,"d":"10.d"},"2020-04-07T08:00:00","2020-04-20T17:00:00","23"]
[25,"组件设计开发",{"v":20,"d":"20.d"},"2020-04-21T08:00:00","2020-05-18T17:00:00","22"]
[26,"设计开发",{"v":10,"d":"10.d"},"2020-04-21T08:00:00","2020-05-04T17:00:00"]
[27,"组件性能测试",{"v":10,"d":"10.d"},"2020-05-05T08:00:00","2020-05-18T17:00:00","26"]
[28,"软硬件通信模式设计开发",{"v":20,"d":"20.d"},"2020-05-19T08:00:00","2020-06-15T17:00:00","25"]
[29,"设计开发",{"v":10,"d":"10.d"},"2020-05-19T08:00:00","2020-06-01T17:00:00"]
[30,"通信性能测试",{"v":10,"d":"10.d"},"2020-06-02T08:00:00","2020-06-15T17:00:00","29"]
[31,"综合测试",{"v":10,"d":"10.d"},"2020-06-16T08:00:00","2020-06-29T17:00:00","28"]
[32,"Transition",{"v":15,"d":"15.d"},"2020-06-30T08:00:00","2020-07-20T17:00:00"]
[33,"综合联调（ThreePart diagnosis）",{"v":10,"d":"10.d"},"2020-06-30T08:00:00","2020-07-13T17:00:00","31"]
[34,"发布（first release）",{"v":5,"d":"5.d"},"2020-07-14T08:00:00","2020-07-20T17:00:00","33"]

{"sheet":"Measurement","index":1,"n_rows":36,"n_cols":6,"rows_kept":36,"merged":[[0,0,0,24]],"flags":["formulas_cached_only"]}
["Measurement Task Estimate"]
["No.","task","Time cost","start","end","pretask"]
[1,"Inception（Project Scope）",{"v":50,"d":"50.d"},"2019-10-29T08:00:00","2020-01-06T17:00:00"]
[2,"Requirment Gether",{"v":10,"d":"10.d"},"2019-10-29T08:00:00","2019-11-11T17:00:00"]
[3,"Preliminary Architecture",{"v":5,"d":"5.d"},"2019-11-12T08:00:00","2019-11-18T17:00:00",2]
[4,"Important Software operation scenario（Use Case）",{"v":20,"d":"20.d"},"2019-11-19T08:00:00","2019-12-16T17:00:00",3]
[5,"UI Prototype（simple user manual)",{"v":10,"d":"10.d"},"2019-11-19T08:00:00","2019-12-02T17:00:00"]
[6,"Operate Path （Happy path of use case）",{"v":10,"d":"10.d"},"2019-12-03T08:00:00","2019-12-16T17:00:00",5]
[7,"Create Preliminary Model",{"v":10,"d":"10.d"},"2019-12-17T08:00:00","2019-12-30T17:00:00",4]
[8,"Class diagram（static Model）",{"v":5,"d":"5.d"},"2019-12-17T08:00:00","2019-12-23T17:00:00"]
[9,"Active diagram（dynamic model）",{"v":5,"d":"5.d"},"2019-12-24T08:00:00","2019-12-30T17:00:00",8]
[10,"Time plan(development schedule)",{"v":5,"d":"5.d"},"2019-12-31T08:00:00","2020-01-06T17:00:00",7]
[11,"Elaboration (Analysis and design)",{"v":55,"d":"55.d"},"2020-01-07T08:00:00","2020-03-23T17:00:00"]
[12,"More software operation scenario (use case)",{"v":20,"d":"20.d"},"2020-01-07T08:00:00","2020-02-03T17:00:00"]
[13,"UI Prototype（simple user manual)",{"v":10,"d":"10.d"},"2020-01-07T08:00:00","2020-01-20T17:00:00",10]
[14,"Operate Path （Happy path of use case）",{"v":10,"d":"10.d"},"2020-01-21T08:00:00","2020-02-03T17:00:00",13]
[15,"Create Detail Model",{"v":20,"d":"20.d"},"2020-02-04T08:00:00","2020-03-02T17:00:00",12]
[16,"Class diagram（static Model）",{"v":10,"d":"10.d"},"2020-02-04T08:00:00","2020-02-17T17:00:00"]
[17,"Active diagram（dynamic model）",{"v":10,"d":"10.d"},"2020-02-18T08:00:00","2020-03-02T17:00:00",16]
[18,"Get the final software structure",{"v":15,"d":"15.d"},"2020-03-03T08:00:00","2020-03-23T17:00:00",15]
[19,"software architecture",{"v":10,"d":"10.d"},"2020-03-03T08:00:00","2020-03-16T17:00:00"]
[20,"software UI",{"v":5,"d":"5.d"},"2020-03-17T08:00:00","2020-03-23T17:00:00",19]
[21,"Construction(coding and testing)",{"v":70,"d":"70.d"},"2020-03-24T08:00:00","2020-06-29T17:00:00"]
[22,"Data base structure design /development",{"v":20,"d":"20.d"},"2020-03-24T08:00:00","2020-04-20T17:00:00"]
[23,"design and development",{"v":10,"d":"10.d"},"2020-03-24T08:00:00","2020-04-06T17:00:00",20]
[24,"performance test",{"v":10,"d":"10.d"},"2020-04-07T08:00:00","2020-04-20T17:00:00",23]
[25,"component design and development",{"v":20,"d":"20.d"},"2020-04-21T08:00:00","2020-05-18T17:00:00",22]
[26,"design and development",{"v":10,"d":"10.d"},"2020-04-21T08:00:00","2020-05-04T17:00:00"]
[27,"performance test",{"v":10,"d":"10.d"},"2020-05-05T08:00:00","2020-05-18T17:00:00",26]
[28,"hardware and software communicate design and development",{"v":20,"d":"20.d"},"2020-05-19T08:00:00","2020-06-15T17:00:00",25]
[29,"design and development",{"v":10,"d":"10.d"},"2020-05-19T08:00:00","2020-06-01T17:00:00"]
[30,"performance test",{"v":10,"d":"10.d"},"2020-06-02T08:00:00","2020-06-15T17:00:00",29]
[31,"General test",{"v":10,"d":"10.d"},"2020-06-16T08:00:00","2020-06-29T17:00:00",28]
[32,"Transition",{"v":15,"d":"15.d"},"2020-06-30T08:00:00","2020-07-20T17:00:00"]
[33,"joint diagnosis（ThreePart diagnosis）",{"v":10,"d":"10.d"},"2020-06-30T08:00:00","2020-07-13T17:00:00",31]
[34,"first release",{"v":5,"d":"5.d"},"2020-07-14T08:00:00","2020-07-20T17:00:00",33]

{"sheet":"SystemToolAndRuleEditor","index":2,"n_rows":74,"n_cols":6,"rows_kept":74,"merged":[[0,0,0,10],[38,0,38,15]],"flags":["formulas_cached_only"]}
["System Tool Task Estimate"]
["No.","task","Time cost","start","end","pretask"]
[1,"Inception（Project Scope）","12 d","2020-01-01","2020-01-16"]
[2,"Requirment Gether","2 d","2020-01-01","2020-01-02"]
[3,"Preliminary Architecture","1 d","2020-01-03","2020-01-03",2]
[4,"Important Software operation scenario（Use Case）","3 d","2020-01-06","2020-01-08",3]
[5,"UI Prototype（simple user manual)","2 d","2020-01-06","2020-01-07"]
[6,"Operate Path （Happy path of use case）","1 d","2020-01-08","2020-01-08",5]
[7,"Create Preliminary Model","4 d","2020-01-09","2020-01-14",4]
[8,"Class diagram（static Model）","2 d","2020-01-09","2020-01-10"]
[9,"Active diagram（dynamic model）","2 d","2020-01-13","2020-01-14",8]
[10,"Time plan(development schedule)","2 d","2020-01-15","2020-01-16",7]
[11,"Elaboration (Analysis and design)","12 d","2020-01-17","2020-02-03"]
[12,"More software operation scenario (use case)","4 d","2020-01-17","2020-01-22"]
[13,"UI Prototype（simple user manual)","2 d","2020-01-17","2020-01-20",10]
[14,"Operate Path （Happy path of use case）","2 d","2020-01-21","2020-01-22",13]
[15,"Create Detail Model","4 d","2020-01-23","2020-01-28",12]
[16,"Class diagram（static Model）","2 d","2020-01-23","2020-01-24"]
[17,"Active diagram（dynamic model）","2 d","2020-01-27","2020-01-28",16]
[18,"Get the final software structure","4 d","2020-01-29","2020-02-03",15]
[19,"software architecture","2 d","2020-01-29","2020-01-30"]
[20,"software UI","2 d","2020-01-31","2020-02-03",19]
[21,"Construction(coding and testing)","15 d","2020-02-04","2020-02-24"]
[22,"Data base structure design /development","4 d","2020-02-04","2020-02-07"]
[23,"design and development","2 d","2020-02-04","2020-02-05",20]
[24,"performance test","2 d","2020-02-06","2020-02-07",23]
[25,"component design and development","4 d","2020-02-10","2020-02-13",22]
[26,"design and development","2 d","2020-02-10","2020-02-11"]
[27,"performance test","2 d","2020-02-12","2020-02-13",26]
[28,"hardware and software communicate design and development","4 d","2020-02-14","2020-02-19",25]
[29,"design and development","2 d","2020-02-14","2020-02-17"]
[30,"performance test","2 d","2020-02-18","2020-02-19",29]
[31,"General test","3 d","2020-02-20","2020-02-24",28]
[32,"Transition","3 d","2020-02-25","2020-02-27"]
[33,"joint diagnosis（ThreePart diagnosis）","2 d","2020-02-25","2020-02-26",31]
[34,"first release","1 d","2020-02-27","2020-02-27",33]
[]
[]
["Rule Editor Task Estimate"]
["No.","task","Time cost","start","end","pretask"]
[1,"Inception-Project Scope","25 d","2020-03-02","2020-04-03"]
[2,"Requirment Gether","5 d","2020-03-02","2020-03-06"]
[3,"Preliminary Architecture","2 d","2020-03-09","2020-03-10",2]
[4,"Important Software operation scenario（Use Case）","10 d","2020-03-11","2020-03-24",3]
[5,"UI Prototype（simple user manual)","5 d","2020-03-11","2020-03-17"]
[6,"Operate Path （Happy path of use case）","5 d","2020-03-18","2020-03-24",5]
[7,"Create Preliminary Model","5 d","2020-03-25","2020-03-31",4]
[8,"Class diagram（static Model）","3 d","2020-03-25","2020-03-27"]
[9,"Active diagram（dynamic model）","2 d","2020-03-30","2020-03-31",8]
[10,"Time plan(development schedule)","3 d","2020-04-01","2020-04-03",7]
[11,"Elaboration (Analysis and design)","32 d","2020-04-06","2020-05-19"]
[12,"More software operation scenario (use case)","10 d","2020-04-06","2020-04-17"]
[13,"UI Prototype（simple user manual)","5 d","2020-04-06","2020-04-10",10]
[14,"Operate Path （Happy path of use case）","5 d","2020-04-13","2020-04-17",13]
[15,"Create Detail Model","15 d","2020-04-20","2020-05-08",12]
[16,"Class diagram（static Model）","10 d","2020-04-20","2020-05-01"]
[17,"Active diagram（dynamic model）","5 d","2020-05-04","2020-05-08",16]
[18,"Get the final software structure","7 d","2020-05-11","2020-05-19",15]
[19,"software architecture","5 d","2020-05-11","2020-05-15"]
[20,"software UI","2 d","2020-05-18","2020-05-19",19]
[21,"Construction(coding and testing)","35 d","2020-05-20","2020-07-07"]
[22,"Data base structure design /development","10 d","2020-05-20","2020-06-02"]
[23,"design and development","5 d","2020-05-20","2020-05-26",20]
[24,"performance test","5 d","2020-05-27","2020-06-02",23]
[25,"component design and development","10 d","2020-06-03","2020-06-16",22]
[26,"design and development","5 d","2020-06-03","2020-06-09"]
[27,"performance test","5 d","2020-06-10","2020-06-16",26]
[28,"hardware and software communicate design and development","10 d","2020-06-17","2020-06-30",25]
[29,"design and development","5 d","2020-06-17","2020-06-23"]
[30,"performance test","5 d","2020-06-24","2020-06-30",29]
[31,"General test","5 d","2020-07-01","2020-07-07",28]
[32,"Transition","7 d","2020-07-08","2020-07-16"]
[33,"joint diagnosis（ThreePart diagnosis）","5 d","2020-07-08","2020-07-14",31]
[34,"first release","2 d","2020-07-15","2020-07-16",33]

{"sheet":"Report","index":3,"n_rows":36,"n_cols":6,"rows_kept":36,"merged":[[0,0,0,22]],"flags":["formulas_cached_only"]}
["Report Task Estimate"]
["No.","task","Time cost","start","end","pretask"]
[1,"Inception（Project Scope）","50 d?","2020-07-21","2020-09-28"]
[2,"Requirment Gether","10 d?","2020-07-21","2020-08-03"]
[3,"Preliminary Architecture","5 d?","2020-08-04","2020-08-10",2]
[4,"Important Software operation scenario（Use Case）","20 d?","2020-08-11","2020-09-07",3]
[5,"UI Prototype（simple user manual)","10 d?","2020-08-11","2020-08-24"]
[6,"Operate Path （Happy path of use case）","10 d?","2020-08-25","2020-09-07",5]
[7,"Create Preliminary Model","10 d?","2020-09-08","2020-09-21",4]
[8,"Class diagram（static Model）","5 d?","2020-09-08","2020-09-14"]
[9,"Active diagram（dynamic model）","5 d?","2020-09-15","2020-09-21",8]
[10,"Time plan(development schedule)","5 d?","2020-09-22","2020-09-28",7]
[11,"Elaboration (Analysis and design)","55 d?","2020-09-29","2020-12-14"]
[12,"More software operation scenario (use case)","20 d?","2020-09-29","2020-10-26"]
[13,"UI Prototype（simple user manual)","10 d","2020-09-29","2020-10-12",10]
[14,"Operate Path （Happy path of use case）","10 d?","2020-10-13","2020-10-26",13]
[15,"Create Detail Model","20 d?","2020-10-27","2020-11-23",12]
[16,"Class diagram（static Model）","10 d?","2020-10-27","2020-11-09"]
[17,"Active diagram（dynamic model）","10 d?","2020-11-10","2020-11-23",16]
[18,"Get the final software structure","15 d","2020-11-24","2020-12-14",15]
[19,"software architecture","10 d","2020-11-24","2020-12-07"]
[20,"software UI","5 d","2020-12-08","2020-12-14",19]
[21,"Construction(coding and testing)","70 d?","2020-12-15","2021-03-22"]
[22,"Data base structure design /development","20 d?","2020-12-15","2021-01-11"]
[23,"design and development","10 d?","2020-12-15","2020-12-28",20]
[24,"performance test","10 d?","2020-12-29","2021-01-11",23]
[25,"component design and development","20 d?","2021-01-12","2021-02-08",22]
[26,"design and development","10 d?","2021-01-12","2021-01-25"]
[27,"performance test","10 d?","2021-01-26","2021-02-08",26]
[28,"hardware and software communicate design and development","20 d?","2021-02-09","2021-03-08",25]
[29,"design and development","10 d?","2021-02-09","2021-02-22"]
[30,"performance test","10 d?","2021-02-23","2021-03-08",29]
[31,"General test","10 d?","2021-03-09","2021-03-22",28]
[32,"Transition","15 d?","2021-03-23","2021-04-12"]
[33,"joint diagnosis（ThreePart diagnosis）","10 d?","2021-03-23","2021-04-05",31]
[34,"first release","5 d?","2021-04-06","2021-04-12",33]

{"sheet":"资源_表","index":4,"n_rows":1,"n_cols":12,"rows_kept":1,"hidden":true,"flags":["formulas_cached_only"]}
["标识号","名称","缩写","类型","材料标签","组","电子邮件地址","Windows 用户帐户","最大单位","标准费率","每次使用成本","备注"]

{"sheet":"工作分配_表","index":5,"n_rows":1,"n_cols":5,"rows_kept":1,"hidden":true,"flags":["formulas_cached_only"]}
["任务名称","资源名称","工时完成百分比","工时","单位"]

{"sheet":"信息_表","index":6,"n_rows":10,"n_cols":5,"rows_kept":10,"hidden":true,"flags":["formulas_cached_only"]}
["Microsoft Office Project",null,"模板标识号:","9876543210","(不要编辑)"]
[]
["Microsoft Office Project 是一种项目管理程序，旨在帮助您计划和管理项目以及交流项目信息。"]
[]
["不论您是要完成简单的任务还是要同时处理多个项目中相关联的任务，开始使用和学习 Project 都非常容易。"]
[]
["使用此模板，您可以将数据导出到 Excel 以执行更高级的数字分析。然后，再将项目数据导回到 Project 中以执行标准项目任务，例如:"]
["* 查看甘特图中链接的任务"]
["* 查看给工作组中每个人分配了多少工时"]
["可以很容易地将此信息导回到 Project 中，并且无需重新输入数据就可保持工作。"]