{"text_format":"2","workbook":"xlsx","n_sheets":9,"sheets":["Sheet1","8","7","6","5","4","3","2","1"],"not_rendered":{"charts":0,"images":9,"macros":0,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":52,"n_cols":10,"rows_kept":52,"cut":false,"hidden":false,"merged":[]}
[]
[null,"序号","问题分类","问题描述","提出者","提出日期","修改者","对应日期","对应说明","状态"]
[null,1,"功能实现","预览区域背景色与其他区域背景色一致了，没有相机预览时，没有预览边界，需要将预览区域背景色适当深一点","沙永刚","2022-08-01","王琦","2022-08-03","加深背景颜色","修改完"]
[null,2,null,"点击图片模式后，发生异常","沙永刚","2022-08-01","王琦","2022-08-03","增加相机判断","修改完"]
[null,3,null,"放大倍数下拉框显示的是倍数，不应该是标尺名称，下拉框内容应从配置文件读取","沙永刚","2022-08-01","王琦","2022-08-03",null,"修改完"]
[null,4,null,"标尺，应该显示可选下拉框，下拉框内容为标尺名","沙永刚","2022-08-01","王琦","2022-08-03",null,"修改完"]
[null,5,null,"需要增加一个分辨率表示项（不可输入）","沙永刚","2022-08-01","王琦","2022-08-03",null,"修改完"]
[null,6,null,"需要追加一个测量设置按钮，弹出测量设置画面","沙永刚","2022-08-01","王琦","2022-08-03",null,"修改完"]
[null,7,null,"改变画面尺寸后，画面布局不合理。建议该画面可以最大化（无最小化）","沙永刚","2022-08-01","王琦","2022-08-03",null,"修改完"]
[null,8,null,"重新测量按钮的图标不易理解，可以换成类似带返回复原箭头的图标","沙永刚","2022-08-01","王琦","2022-08-03",null,"修改完"]
[null,9]
[null,10]
[null,11]
[null,12]
[null,13]
[null,14]
[null,15]
[null,16]
[null,17]
[null,18]
[null,19]
[null,20]
[null,21]
[null,22]
[null,23]
[null,24]
[null,25]
[null,26]
[null,27]
[null,28]
[null,29]
[null,30]
[null,31]
[null,32]
[null,33]
[null,34]
[null,35]
[null,36]
[null,37]
[null,38]
[null,39]
[null,40]
[null,41]
[null,42]
[null,43]
[null,44]
[null,45]
[null,46]
[null,47]
[null,48]
[null,49]
[null,50]

{"sheet":"8","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"7","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"6","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"5","index":4,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"4","index":5,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"3","index":6,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"2","index":7,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"1","index":8,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}