{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["Sheet1","1","2"],"not_rendered":{"charts":0,"images":3,"macros":0,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":52,"n_cols":10,"rows_kept":52,"cut":false,"hidden":false,"merged":[]}
[]
[null,"序号","问题分类","问题描述","提出者","提出日期","修改者","对应日期","对应说明","状态"]
[null,1,"功能实现","图片来源项目图库时，选择最后一个项目，点击确认时发生异常","沙永刚","2022-08-02","王琦","2022-08-02","序号获取错误","修改完"]
[null,2,null,"根据职责单一原则，该画面只负责选择项目，不应参与其他业务逻辑处理，因此不在该画面调用业务逻辑的处理功能，该画面只需要公开属性TestingId（其他属性如必要也可公开）即可，点击继续按钮后，由前一画面完成后续处理","沙永刚","2022-08-19","王琦","2022-08-22","将窗体不在任务栏显示即可。代码为\nShowInTaskbar = false;","修改完"]
[null,3]
[null,4]
[null,5]
[null,6]
[null,7]
[null,8]
[null,9]
[null,10]
[null,11]
[null,12]
[null,13]
[null,14]
[null,15]
[null,16]
[null,17]
[null,18]
[null,19]
[null,20]
[null,21]
[null,22]
[null,23]
[null,24]
[null,25]
[null,26]
[null,27]
[null,28]
[null,29]
[null,30]
[null,31]
[null,32]
[null,33]
[null,34]
[null,35]
[null,36]
[null,37]
[null,38]
[null,39]
[null,40]
[null,41]
[null,42]
[null,43]
[null,44]
[null,45]
[null,46]
[null,47]
[null,48]
[null,49]
[null,50]

{"sheet":"1","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"2","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}