{"text_format":"2","workbook":"xlsx","n_sheets":5,"sheets":["Sheet1","1","3","M3","4"],"not_rendered":{"charts":0,"images":3,"macros":0,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":51,"n_cols":10,"rows_kept":51,"cut":false,"hidden":false,"merged":[]}
[]
[null,"序号","问题分类","问题描述","提出者","提出日期","修改者","对应日期","对应说明","状态"]
[null,1,"功能实现","缺少控制Z轴移动按钮","沙永刚","2022-08-01","王琦","2022-08-02","详见Sheet[M3]","修改完"]
[null,2,null,"未连接相机时，点击拍照设置相关按钮时发生异常","沙永刚","2022-08-01","王琦","2022-08-02","增加判断","修改完"]
[null,3,null,"画面Layout参照Sheet[3]修改","沙永刚","2022-08-02","王琦","2022-08-02","详见Sheet[M3]","修改完"]
[null,4,null,"该画面不需要测量和保存，需要添加确定和取消按钮","沙永刚","2022-08-02","王琦","2022-08-02","详见Sheet[M3]","修改完"]
[null,6]
[null,7]
[null,8]
[null,9]
[null,10]
[null,11]
[null,12]
[null,13]
[null,14]
[null,15]
[null,16]
[null,17]
[null,18]
[null,19]
[null,20]
[null,21]
[null,22]
[null,23]
[null,24]
[null,25]
[null,26]
[null,27]
[null,28]
[null,29]
[null,30]
[null,31]
[null,32]
[null,33]
[null,34]
[null,35]
[null,36]
[null,37]
[null,38]
[null,39]
[null,40]
[null,41]
[null,42]
[null,43]
[null,44]
[null,45]
[null,46]
[null,47]
[null,48]
[null,49]
[null,50]

{"sheet":"1","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"M3","index":3,"n_rows":1,"n_cols":1,"rows_kept":1,"cut":false,"hidden":false,"merged":[]}
[5]

{"sheet":"4","index":4,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}