{"text_format":"2","workbook":"xlsx","n_sheets":12,"sheets":["Sheet1","1","2","3","4","5","6","7","8","9","10","11"],"not_rendered":{"charts":0,"images":12,"macros":0,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":52,"n_cols":10,"rows_kept":52,"cut":false,"hidden":false,"merged":[]}
[]
[null,"序号","问题分类","问题描述","提出者","提出日期","修改者","对应日期","对应说明","状态"]
[null,1,"功能实现","画面没有对邮箱输入的合法性进行Check","沙永刚","2022-08-08","沙永刚","2022-08-31",null,"修改完"]
[null,2,null,"公司LOGO应该可选择常用图片格式文件，而不会是icon文件","沙永刚","2022-08-08","沙永刚","2022-08-31","删除LOGO","修改完"]
[null,3,null,"省份和程序，应从ComboBox中选择，不应可自由输入","沙永刚","2022-08-08","沙永刚","2022-08-31",null,"修改完"]
[null,4,null,"窗口尺寸可改变（不应改变）","沙永刚","2022-08-08","沙永刚","2022-08-31",null,"修改完"]
[null,5,null,"画面必须输入项不可以为空，确定时需要进行必要的Check","沙永刚","2022-08-08","沙永刚","2022-08-31",null,"修改完"]
[null,6,null,"画面关闭时，不应使用Close，为设定DialogResult结果","沙永刚","2022-08-08","沙永刚","2022-08-31",null,"修改完"]
[null,7,null,"代码中使用了硬编码，需要修改到资源文件中","沙永刚","2022-08-08","沙永刚","2022-08-31",null,"修改完"]
[null,8,null,"代码注释不符合规范","沙永刚","2022-08-08","沙永刚","2022-08-31",null,"修改完"]
[null,9,null,"Tab键顺序未遵循从左到右，从上到下的顺序，需要调整","沙永刚","2022-08-08","沙永刚","2022-08-31",null,"修改完"]
[null,10,null,"在代码中使用固定用户ID来取用户信息了，应该从数据库中取得默认第一个即可","沙永刚","2022-08-08","沙永刚","2022-08-31","不在使用数据库表，而是使用xml配置文件","修改完"]
[null,11,null,"初始化及点击确定按钮未考考虑数据库无数据的情况","沙永刚","2022-08-08","沙永刚","2022-08-31","不在使用数据库表，而是使用xml配置文件","修改完"]
[null,12]
[null,13]
[null,14]
[null,15]
[null,16]
[null,17]
[null,18]
[null,19]
[null,20]
[null,21]
[null,22]
[null,23]
[null,24]
[null,25]
[null,26]
[null,27]
[null,28]
[null,29]
[null,30]
[null,31]
[null,32]
[null,33]
[null,34]
[null,35]
[null,36]
[null,37]
[null,38]
[null,39]
[null,40]
[null,41]
[null,42]
[null,43]
[null,44]
[null,45]
[null,46]
[null,47]
[null,48]
[null,49]
[null,50]

{"sheet":"1","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"2","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"3","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"4","index":4,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"5","index":5,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"6","index":6,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"7","index":7,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"8","index":8,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"9","index":9,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"10","index":10,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"11","index":11,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}