{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["任务"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"任务","index":0,"n_rows":9,"n_cols":7,"rows_kept":9,"cut":false,"hidden":false,"merged":[]}
[]
[null,"No","任务","目标","成果物","负责人","期限"]
[null,1,"原型修改","修改原型，修改后，相关人员会议审查，确认后使用该原型指导开发","原型画面及概要说明（原型中备注）","宋珊珊"]
[null,2,"Metis2.0调研","1.结合原型功能，调研在Metis2.0开发方法（包括菜单及UI布局）\n2.调查清洁度原型画面哪些已经在Metis2.0中存在，哪些需要修改后使用","1.UI概要说明文档（图示方式即可）\n2.原型画面开发概要说明（对照Metis2.0画面）","王琦"]
[null,3,"软件概要说明","整理出软件全部画面，并对每个画面功能进行概要说明","软件功能概要说明","沙永刚"]
[null,4,"数据设计","考虑测试结果的结构化存储，及为日后的数据集中存储提供支撑","数据库设计说明书","沙永刚、宋珊珊、王琦"]
[null,5,"工作量估算","对每个画面的工作量进行估算（需要考虑无画面隐含功能）","工作量估算文档","沙永刚、宋珊珊、王琦"]
[null,6,"硬件确认","针对哪些硬件开发，何时到位：\n显微镜、载物台、相机、物镜、偏光镜、滤膜样品、相关控制器",null,"王新贺"]
[null,7,"相关会议","4月14日会议相关问题确认（林斌），后续确认结果会议沟通安排",null,"王新贺"]