{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["问题列表"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"问题列表","index":0,"n_rows":27,"n_cols":8,"rows_kept":27,"cut":false,"hidden":false,"merged":[[1,2,1,3],[2,2,2,3],[3,2,3,3]]}
[]
[null,"会议","清洁度会议"]
[null,"时间","2022/9/22 09:00-12:00"]
[null,"人员","王新贺、林斌、宋珊珊、刘洪冰、王琦、沙永刚"]
[null,"No","模块","内容","结论","提出者","责任者","状态"]
[null,1,"检测","测量计算大量使用CPU会不会导致硬件扫描精度及速度","需要结合硬件确认",null,"王琦","持续优化"]
[null,2,"检测","扫描后的测量及统计分析，需要持续优化性能","分析算法耗时瓶颈，调研合理使用CPU、GPU",null,"王琦、沙永刚","持续优化"]
[null,3,"检测","图库模式需要添加数据更新按钮；颗粒编辑画面，点击完成后，性能略卡；","颗粒编辑确定后，直接进行测量，但不进行统计分析，统计分析需要在点击数据更新后进行",null,"王琦"]
[null,5,"检测","颗粒分割后，颗粒类型应当自动重新分析","需要确认：被分割后的颗粒，其颗粒类型应是重新分析的",null,"王琦","完成"]
[null,8,"检测","替换图片功能","使用高倍率拍照，替换报告中图片，是否可修改等操作需调研确认",null,"王琦","二期"]
[null,7,"算法","颗粒编辑-分割、连接、增大、缩小，UI操作","暂时OK，后续林斌有更好的方式时再进行调研或修改",null,"刘洪冰","完成"]
[null,11,"规程","ISO4406、ISO4407、ISO16232、VDA19.2","需要提供各个标准的分级设定文档（其他差异需要说明）",null,"林斌、沙永刚"]
[null,9,"算法","平均灰度必须所有点参与计算","需要确认现状",null,"沙永刚","完成"]
[null,6,"检测","实时预览窗口，需要能够根据不同颗粒动态刷新","即实时预览窗口在最上层显示，图库模式下，选择不同的颗粒，实时预览应实时定位选择的颗粒位置",null,"沙永刚","完成"]
[null,10,"规程","VDA19.2标准差异未实现","先期理解、可二期迭代实现",null,"沙永刚","二期"]
[null,12,"规程","分析范围需要提供用户交互功能，拼图后让用户指定范围（鼠标移动）","需要在算法测量前，先得出缩略图，以便确定范围",null,"沙永刚","完成"]
[null,13,"规程","阈值设定需要交互（大图加载）","性能问题：大图加载；及二值化轮廓提取",null,"沙永刚","二期"]
[null,14,"规程","规程设置-阈值设定性能优化（考虑使用单独只分析轮廓函数）","需要算法测提供单独轮廓识别函数",null,"沙永刚","完成"]
[null,15,"规程","规程新建不要，只保留克隆；系统内置不同标准规程（不可删除）","规程树增加标准规程跟节点，且不可删除",null,"沙永刚","完成"]
[null,16,"规程","规程设置中，碎屑删除系统内置最小值5（需要后门可修改）","需要可通过配置文件进行最小值设定（画面不可见）",null,"沙永刚","完成"]
[null,17,"检测","参数设定，灰度差为或的关系","灰度差为或的关系",null,"沙永刚","完成"]
[null,18,"规程","只有明场图片，需要腐蚀与膨胀？","不需要考虑只有明场场合",null,"沙永刚","完成"]
[null,21,"设置","需要磁盘清理功能","先期可跳转到图片路径",null,"沙永刚","完成，二期实现自动清理"]
[null,19,"报告","报告中数量，以使用归一化参数为准","报告中需要使用归一化的数量",null,"宋珊珊","完成"]
[null,20,"报告","CCC编码，需要追加到报告中","放到颗粒信息块内，单独占一行",null,"宋珊珊","完成"]
[null,19,"报告","合并的报告模板作成","合并报告的模板，不同处：滤膜概图为多个被合并滤膜概图",null,"宋珊珊","完成"]
[null,19,"报告","合并的报告的数据及图片提取方法实现","合并的报告的数据及图片提取方法实现",null,"宋珊珊","完成"]