{"text_format":"2","workbook":"xlsx","n_sheets":2,"sheets":["交叉测试进度一览","综合测试计划"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"交叉测试进度一览","index":0,"n_rows":45,"n_cols":10,"rows_kept":45,"cut":false,"hidden":false,"merged":[[0,6,0,7]]}
[{"$nulls":6},{"$f":"\"总：\"&SUM(G3:G162)&\"人日\"&\" = \"&ROUND(SUM(G3:G162)/20,2)&\"人月\"","v":"总：30人日 = 1.5人月"}]
[null,"No","功能模块","画面名","表示方式","主要测试点","工作量","责任者","计划期限","备注"]
[null,{"$f":"ROW()-2","v":1},"检测分析","共通",null,"所有界面共用的测试内容",0.5,"宋珊珊","2023-01-05"]
[null,{"$f":"ROW()-2","v":2},null,"单滤膜相机扫描模式",null,null,0.5,"宋珊珊","2023-01-05"]
[null,3,null,"检测",null,"（1）相机扫描检测\n（2）本地图片检测",1.5,"宋珊珊","2023/1/6-2023/1/9","相机扫描检测需等0.7接口到公司后可开始测试"]
[null,4,null,"规程选择","-",null,0.5,"宋珊珊","2023-01-09"]
[null,5,null,"检测信息录入","-",null,1,"宋珊珊","2023-01-10"]
[null,6,null,"分析范围设定",null,"范围设定的值对执行效率的影响测试、设定值过大是否支持",0.5,"宋珊珊","2023-01-11"]
[null,7,null,"物相提取设定","弹出","扫描检测和离线检测两种情况下界面显示内容不同，按规程分别测试",1,"宋珊珊","2023-01-11"]
[null,8,null,"图库模式","弹出",null,2,"宋珊珊","2023/1/12---2023/1/13"]
[null,9,null,"颗粒编辑","-",null,1,"宋珊珊","2023-01-16"]
[null,10,null,"高度测量",null,null,0.5,"宋珊珊","2023-01-17"]
[null,11,null,"分级模式",null,null,1,"宋珊珊","2023-01-18"]
[null,12,"规程管理","共通","工作区","所有界面共用的测试内容",0.7,"王琦","2023-01-05"]
[null,13,null,"规程浏览","弹出",null,1,"王琦","2023-01-06"]
[null,14,null,"基本信息",null,null,0.2,"王琦","2023-01-05"]
[null,15,null,"图片来源","弹出","(1)分为相机扫描和本地图片两种情况，需要分别对应测试\n(2)涉及硬件配置需在测试",1.5,"王琦","2023/1/9---2023/1/10"]
[null,16,null,"拼图详细设置","弹出","不同设定下拼图效果、及执行效率测试",1,"王琦","2023-01-11"]
[null,17,null,"信息模板","弹出",null,1,"王琦","2023-01-12"]
[null,18,null,"标签选择",null,null,0.3,"王琦","2023-01-10"]
[null,19,null,"执行流程",null,"包含“分析范围”设定与“物相提取”两部分",1,"王琦","2023-01-13"]
[null,20,null,"参数设置","发现人","参数修改对检测结果的影响测试",1,"王琦","2023-01-16"]
[null,21,null,"分级设置",null,null,2,"王琦","2023/1/17---2023/1/18"]
[null,22,null,"清洁度编码",null,null,0.8,"王琦","2023-01-19"]
[null,23,null,"报告选项",null,null,0.7,"王琦","2023-01-20"]
[null,24,"项目管理","共通","弹出","所有界面共用的测试内容",0.3,"王琦","2023-01-20"]
[null,25,null,"项目浏览",null,"包括项目的编辑功能",2,"王琦","2023/1/28---2023/1/29"]
[null,26,null,"项目合并",null,null,0.7,"王琦","2023-01-30"]
[null,27,"系统设置","共通","弹出","所有界面共用的测试内容",0.8,"王琦","2023-01-31"]
[null,28,null,"通常设置","弹出",null,0.7,"王琦","2023-01-31"]
[null,29,null,"聚焦参数",null,"调用Metis功能",0.1,"王琦","2023-01-30"]
[null,30,null,"物镜转盘","工作区",null,0.4,"王新贺","2023-01-09"]
[null,31,null,"存储设置","弹出",null,0.5,"王新贺","2023-01-09"]
[null,32,null,"磁盘清理","工作区",null,0.3,"王新贺","2023-01-10"]
[null,33,null,"实验室","弹出",null,0.4,"王新贺","2023-01-10"]
[null,34,null,"用户管理",null,null,0.5,"王新贺","2023-01-11"]
[null,35,null,"客户管理",null,null,0.5,"王新贺","2023-01-11"]
[null,36,null,"部件管理","工作区",null,0.5,"王新贺","2023-01-12"]
[null,37,null,"权限管理",null,null,0.3,"王新贺","2023-01-12"]
[null,38,null,"标尺标定",null,"调用Metis功能",0.2,"王新贺","2023-01-12"]
[null,39,null,"标尺样式",null,"调用Metis功能",0.1,"王新贺","2023-01-13"]
[null,40,null,"测量设置",null,"调用Metis功能",0.1,"王新贺","2023-01-13"]
[null,41,null,"快捷键",null,"调用Metis功能",0.2,"王新贺","2023-01-13"]
[null,42,"帮助","共通",null,null,0.1,"王新贺","2023-01-13"]
[null,43,null,"关于画面",null,null,0.1,"王新贺","2023-01-13"]

{"sheet":"综合测试计划","index":1,"n_rows":46,"n_cols":10,"rows_kept":46,"cut":false,"hidden":false,"merged":[[0,6,0,7]]}
[{"$nulls":6},{"$f":"\"总：\"&SUM(G3:G164)&\"人日\"&\" = \"&ROUND(SUM(G3:G164)/20,2)&\"人月\"","v":"总：30.2人日 = 1.51人月"}]
[null,"No","功能模块","画面名","表示方式","主要测试点","工作量","责任者","计划期限","备注"]
[null,{"$f":"ROW()-2","v":1},"检测分析","共通",null,"所有界面共用的测试内容",0.5,"杨欣瑜","2023-01-05"]
[null,{"$f":"ROW()-2","v":2},null,"单滤膜相机扫描模式",null,null,0.5,"杨欣瑜","2023-01-05"]
[null,3,null,"检测",null,"（1）相机扫描检测\n（2）本地图片检测",1.5,"杨欣瑜","2023/1/6-2023/1/9","相机扫描检测需等0.7接口到公司后可开始测试"]
[null,4,null,"规程选择","-",null,0.5,"杨欣瑜","2023-01-09"]
[null,5,null,"检测信息录入","-",null,1,"杨欣瑜","2023-01-10"]
[null,6,null,"分析范围设定",null,"范围设定的值对执行效率的影响测试、设定值过大是否支持",0.5,"杨欣瑜","2023-01-11"]
[null,7,null,"物相提取设定","弹出","扫描检测和离线检测两种情况下界面显示内容不同，按规程分别测试",1,"杨欣瑜","2023-01-11"]
[null,8,null,"图库模式","弹出",null,2,"杨欣瑜","2023/1/12---2023/1/13"]
[null,9,null,"颗粒编辑","-",null,1,"杨欣瑜","2023-01-16"]
[null,10,null,"高度测量",null,null,0.5,"杨欣瑜","2023-01-17"]
[null,11,null,"分级模式",null,null,1,"杨欣瑜","2023-01-18"]
[null,12,"规程管理","共通","工作区","所有界面共用的测试内容",0.7,"杨欣瑜","2023-01-19"]
[null,13,null,"规程浏览","弹出",null,1,"杨欣瑜","2023-01-20"]
[null,14,null,"基本信息",null,null,0.2,"杨欣瑜","2023-01-19"]
[null,15,null,"图片来源","弹出","(1)分为相机扫描和本地图片两种情况，需要分别对应测试\n(2)涉及硬件配置需在测试",1.5,"杨欣瑜","2023/1/28---2023/1/29"]
[null,16,null,"拼图详细设置","弹出","不同设定下拼图效果、及执行效率测试",1,"杨欣瑜","2023-01-30"]
[null,17,null,"信息模板","弹出",null,1,"杨欣瑜","2023-01-31"]
[null,18,null,"标签选择",null,null,0.3,"杨欣瑜","2023-02-01"]
[null,19,null,"执行流程",null,"包含“分析范围”设定与“物相提取”两部分",1,"杨欣瑜","2023-02-01"]
[null,20,null,"参数设置","发现人","参数修改对检测结果的影响测试",1,"杨欣瑜","2023-02-02"]
[null,21,null,"报告选项",null,null,0.7,"杨欣瑜","2023-02-03"]
[null,22,null,"分级设置",null,null,2,"杨欣瑜","2023/2/6---2023/2/7"]
[null,23,null,"清洁度编码",null,null,0.8,"杨欣瑜","2023-02-08"]
[null,24,"项目管理","共通","弹出","所有界面共用的测试内容",0.3,"杨欣瑜","2023-02-09"]
[null,25,null,"项目浏览",null,"包括项目的编辑功能",2,"杨欣瑜","2023/2/9---2023/2/10"]
[null,26,null,"项目合并",null,null,0.7,"杨欣瑜","2023-02-13"]
[null,27,"系统设置","共通","弹出","所有界面共用的测试内容",0.8,"杨欣瑜","2023-02-14"]
[null,28,null,"聚焦参数",null,"调用Metis功能",0.1,"杨欣瑜","2023-02-14"]
[null,29,null,"通常设置","弹出",null,0.7,"杨欣瑜","2023-02-15"]
[null,30,null,"物镜转盘","工作区",null,0.4,"杨欣瑜","2023-02-15"]
[null,31,null,"磁盘清理","工作区",null,0.3,"杨欣瑜","2023-02-15"]
[null,32,null,"存储设置","弹出",null,0.5,"杨欣瑜","2023-02-16"]
[null,33,null,"实验室","弹出",null,0.4,"杨欣瑜","2023-02-16"]
[null,34,null,"用户管理",null,null,0.5,"杨欣瑜","2023-02-17"]
[null,35,null,"客户管理",null,null,0.5,"杨欣瑜","2023-02-17"]
[null,36,null,"部件管理","工作区",null,0.5,"杨欣瑜","2023-02-20"]
[null,37,null,"权限管理",null,null,0.3,"杨欣瑜","2023-02-20"]
[null,38,null,"标尺标定",null,"调用Metis功能",0.2,"杨欣瑜","2023-02-20"]
[null,39,null,"标尺样式",null,"调用Metis功能",0.1,"杨欣瑜","2023-02-21"]
[null,40,null,"测量设置",null,"调用Metis功能",0.1,"杨欣瑜","2023-02-21"]
[null,41,null,"快捷键",null,"调用Metis功能",0.2,"杨欣瑜","2023-02-21"]
[null,42,"帮助","共通",null,null,0.1,"杨欣瑜","2023-02-21"]
[null,43,null,"目录",null,null,0.2,"杨欣瑜","2023-02-08","操作手册未完成，暂时无法测试。后续完成测试"]
[null,44,null,"关于画面",null,null,0.1,"杨欣瑜","2023-02-21"]